## SR
FISHWAY STATUS REPORT | [6 empty] | JOHN DAY DAM
Date: | 2011-11-20 | [7 empty] | JD/WC Project-Fisheries
Inspection Period: |  | 11/13/11 thru 11/19/11 | 2011-11-19 | [5 empty] | P.O. Box 564
Rufus, OR 97050
Phone: 541-506-3800
Fishway inspections twice daily.
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  | 14 | Temperature: |  | 51.5714 | F
|  |  | Out of Criteria | Limit | Comments |  |  | Secchi: | 6 | Ft.
NORTH FISHWAY |  |  |  |  | OOS and dewatered since 7 November. ETR mid March 2012.
Exit differential |  |  | N/A | ≤ 0.5'
Exit Control weirs |  |  | N/A | Per forebay
Count station differential |  |  | N/A | ≤ 0.3'
Weir crest depth |  |  | N/A | 1.0' ± 0.1'
Entrance differential |  |  | N/A | 1.0' - 2.0' | AVG | #DIV/0!
Entrance weir EW1 |  |  | N/A | depth (≥ 8') | AVG | #DIV/0!
Entrance weir EW2 |  |  | N/A | No criteria
SOUTH FISHWAY |  |  |  |  | 2 AWS turbine operation; turbine 3 overhaul continues with ETR January 2012
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for MID forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
South entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | 2.2143
Entrance weir SE1 |  |  | 0 | depth (≥ 8') | AVG | 8.7571
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | AVG
Bay 1 differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.5929
N.entrance PH(Bay 19)differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.3786
Entrance weir NE1 |  |  | 0 | depth (≥ 8') | AVG | 8.4143
Entrance weir NE2 |  |  | 0 | depth (≥ 8') | AVG | 8.4786
JUVENILE PASSAGE
Forebay/bypass conduit differential |  |  | 0 | 4.0' - 5.0' | AVG | 4.5846
Submersible traveling screens |  |  | 0 | visual inspect | All STSs are working properly
Turbine trashrack drawdown |  |  | 0 | <1.5', wkly | No discrepancies.
Vert barrier screen drawdown |  |  | 0 | <1.5', wkly | No discrepancies
Spill volume |  |  | None | per FPP | Spill from bay 2 ended on 11/3 (due to North fishway dewatering.)
Spill pattern |  |  | N/A | per FPP
Turbine Unit Priority |  |  | 0 | per FPP
Turbine 1% Efficiency |  |  | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: OOS for winter maintenance. Fully dewatered on 11/17 due to a freezing weather forecast. ETR 1 April 2012
Maintenance: All flushing water pipes/valves were dewatered and SMF fully winterized by 11/18 PM.
Research: None
OTHER ISSUES:
Birds: see bird tab.
JD tailrace BRZ Avian Lines repair and improvements' contract is ongoing. All 125 lines will be available/properly tensioned for the 2012 juvenile passage
season starting on 1 April. JD Engineering and Fisheries are involved in its coordination as needed.
Operations:
JD North fishway was successfully dewatered on 11/7- 9. AWS electric pumps were turned off on 11/4 am to minimize a number of fish needing salvage
on the day of dewatering; it worked well since only 3 adult salmonids total were observed and none had to be handled on 11/7.
JD South fishway remains in regular service and is meeting all FPP criteria. Scheduled for dewatering on 1/23/2012.
New construction:
Construction of a building for the future JD NFL AWS pumps ' electrical substation continues on the pump deck (downstream of Navlock.)
JD North entrance improvements' contract was awarded to Slayden Group at almost $ 6 million on 9/15. The contractor's mobilization activities
commenced on 11/7 November. ETR is mid March 2012. JD Engineering and Fisheries participate in weekly coordination meetings.
JD South AWS turbine 3 rehab continues on schedule. ETR is January, 2012. JD Maintenance is providing the contractor's support.
Maintenance:
November STSs' video inspection delayed to the week of 11/21, it will be the last one for 2011 passage season ending on 12/15.
MU1 C trashrack's diving to clean its top ledge was performed on 11/1. The top segments need to be removed for their repairs soon.
However, the trashrack crane's clutch failed on 11/1 and it may take up to 4 months to repair due to long lead time for the necessary parts.
The MU 1 C trashracks can't be lifted until the crane is fixed.
JD South Fishway Automation is in service.
Gatewell drawdown: Conducted. All VBSs OK. All MU trashracks are raked as soon as their differential reaches 1.3' or higher.
Calibration: | 11/19/2011 All PLCs were accurate with a reading error of less than 0.3 '.
Research:
Information meeting for the 2012 JD fish research season took place on 11/3. Mr. Schwartz, Portland District bio and PNNL managers described their
planned scope of work; the JD project support needs were discussed and planning is underway.
PNNL crew removed their hydrophones from JD powerhouse and spillway's pier noses by 9/28. Planning for 2012 season's underway.
U of I continues with adult lamprey PIT detections at both JD ladders.

## FishCounts
John Day 2011
114 Full Flow PIT tag detections so far this month.

## Birds
S2:no birds observed
S1: no birds observed
S3:no birds
observed
P4: 200 gulls
50 grebe
P3: 20 cormorant 80 gulls,
P2: no birds observed
P1: no birds observed
S4: 500 gulls

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fallbacks
Sun | 53 |  | 6 |  | 0
Mon | 53 |  | 6 |  | 0
Tues | 53 |  | 6 |  | 0
Wed | 51 |  | 6 |  | 0
Thur | 51 |  | 6 |  | 0
Fri | 50 |  | 6 |  | 0
Sat | 50 |  | 6 |  | 0
AVG: | 51.5714 | AVG: | 6 | AVG | 0
|  |  |  | MAX | 0
|  |  |  | MIN | 0
| NE1 | NE2 | S.Ent | SE1 | N.Ent | EW1 | JBS Diff | Bay1 | Bay19
Sun | 8.3 | 8.2 | 1.3 | 8.7 | oos | oos | 4.6 | 1.7 | 1.6
Sun | 8.3 | 8.4 | 1.3 | 8.6 | oos | oos | 4.6 | 1.8 | 1.5
Mon | 8.2 | 8.1 | 1.3 | 8.3 | oos | oos | 4.5 | 1.6 | 1.3
Mon | 8.6 | 8.5 | 1 | 9 | oos | oos | 4.5 | 1.4 | 1.3
Tues | 8.3 | 8.5 | 1.1 | 8.9 | oos | oos | 4.5 | 1.4 | 1.2
Tues | 8.2 | 8 | 1.6 | 8.1 | oos | oos | 4.6 | 1.2 | 1.2
Wed | 8.6 | 8.8 | 1.2 | 8.9 | oos | oos | 4.8 | 1.5 | 1.2
Wed | 9.5 | 9.5 | 1.3 | 8.6 | oos | oos | 4.6 | 1.7 | 1.5
Thur | 8.4 | 8.6 | 1 | 9.1 | oos | oos | 4.6 | 1.4 | 1.3
Thur | 8.2 | 8.4 | 1.5 | 8.4 | oos | oos |  | 1.7 | 1.6
Fri | 8.4 | 8.5 | 14.3 | 9 | oos | oos | 4.6 | 1.7 | 1.1
Fri | 8.3 | 8.5 | 1.3 | 9 | oos | oos | 4.6 | 1.7 | 1.7
Sat | 8.4 | 8.6 | 1.5 | 9 | oos | oos | 4.6 | 1.8 | 1.1
Sat | 8.1 | 8.1 | 1.3 | 9 | oos | oos | 4.5 | 1.7 | 1.7
AVG: | 8.4143 | 8.4786 | 2.2143 | 8.7571 | #DIV/0! | #DIV/0! | 4.5846 | 1.5929 | 1.3786