## SR
FISHWAY STATUS REPORT | [6 empty] | JOHN DAY DAM
Date: | 2010-12-22 | [7 empty] | JD/WC Project-Fisheries
Inspection Period: |  | 12/12 thru 12/18/2010 | [6 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541-506-3800
Fishway inspections once a day in winter.
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  | 7 | Temperature: |  | 43.5714 | F
|  |  | Out of Criteria | Limit | Comments |  |  | Secchi: | 6 | Ft.
NORTH FISHWAY |  |  |  |  | Dewatered on 12/2/10. Returning back to service at the end of January, 2011.
Exit differential |  |  |  | ≤ 0.5'
Exit Control weirs |  |  |  | Per forebay
Count station differential |  |  |  | ≤ 0.3'
Weir crest depth |  |  |  | 1.0' ± 0.1'
Entrance differential |  |  |  | 1.0' - 2.0'
Entrance weir EW1 |  |  |  | depth (≥ 8')
Entrance weir EW2 |  |  |  | No criteria
SOUTH FISHWAY |  |  |  |  | Scheduled to be dewatered in early February, after JD North returns back to service.
Exit differential |  |  | 0 | ≤ 0.5'
Exit Control weirs |  |  | 0 | Per forebay | Set for MID forebay
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
South entrance differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.2571
Entrance weir SE1 |  |  | 0 | depth (≥ 8') | AVG | 8.4571
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | AVG
Bay 1 differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.7714
N. Entrance PH(Bay 19)differential |  |  | 0 | 1.0' - 2.0' | AVG | 1.6
Entrance weir NE1 |  |  | 0 | depth (≥ 8') | AVG | 8.4714
Entrance weir NE2 |  |  | 0 | depth (≥ 8') | AVG | 8.3286
JUVENILE BYPASS
Forebay/bypass conduit differential |  |  | 0 | 4.0' - 5.0' | AVG | 4.5857
Submersible traveling screens |  |  | 0 | visual inspect | All STS were pulled for visual inspection in October 2010. No problems were found
Turbine trashrack drawdown |  |  | 0 | <1.5', wkly
Vert barrier screen drawdown |  |  | 0 | <1.5', wkly
Spill volume |  |  | 0 | per FPP | No spill for fish passage until 10 April 2011.
Spill pattern |  |  | 0 | per FPP
Turbine Unit Priority |  |  | 0 | per FPP
Turbine 1% Efficiency |  |  | 0 | per FPP
SMOLT MONITORING FACILITY |  |  | End of season dewatering was on 11/29/10.
Operation: | OOS until the next year's passage season starting on 1 April 2011.
Maintenance:
2010 extended operation resulted in the SMF flushing water pipes and valves being frozen/ cracked. All damages will be repaired before 1 April.
SMF was not designed for freezing temperatures and we request FPOM permission to shut it down earlier next year, after November 15.
PSMFC electrical crew completed updates to the SMF control system, they will allow access to various sampling settings in real time over the internet.
OTHER ISSUES:
JOHN DAY
Birds: | see bird tab
New construction: 15 kV tap's installation by contractor (for the North Ladder's future AWS pumps ) is almost complete.
JD Fisheries participating in JDN entrance improvements' design, surveys and inspections.
BPA approved additional funding for completion of the JD South AWS turbine 3 rehab. Specific plans for this challenging job are formulated by the
Portland District's engineering team in coordination with JD Maintenance. ETR is March 2012.
Maintenance:
JD north fishway was dewatered for annual maintenance on 12/2 and its entrance on 12/8. It is scheduled to return back to service at the end of January.
Its AWS conduit hasn't been dewatered yet due to the dewatering pumps failure. Renting of additional pumps is likely to be necessary.
Over 20 avian lines were noticed to be submerged at the JD tailrace BRZ. PM and Project Management were notified.
South Fishway's automation work on hold due to a temporary shortage of labor at JDE (Electrical) ; expected completion in approximately a month (?)
One out of six North AWS pumps is currently OOS due to the gear box failure. It won’t be repaired/ available during 2011 passage season; all six pumps
are scheduled for replacement the next year. Only three pumps can be in service simultaneously.
Calibration: Conducted on 12/17, all were within established limits. Gatewell drawdown was done 11/28, all are within established limits.
Operations:
Only one adult fishway, JD South is in regular service and is meeting all FPP criteria.
Good news ! North Ladder's CS crowder box window and auto cleaning brush are being currently replaced/ repaired by a contractor. Expected
completion is next week and the JD North counting station will be ready early for 2011 passage season.
JD trashrack gentry remains OOS due to the clutch failure; parts are on order and will be installed as soon as they are received. No problems with
plugged intake trashracks due to the low debris levels during most of 2010 passage season.
The STS inspection with pulled screens was completed by 11/18. All STSs were OK and did not require any repairs.
STS camera device 's old video system failed beyond repair at the end of August inspection. JDE(Electrical) will be replacing it with brand new
cameras / hardware over this winter outage. RTS is May 2011.
All remaining fishways' passage equipment is working well and fully meeting FPP criteria.
Research:
Planning for 2011 research activities is underway.
U of I continues with adult lamprey PIT detections and with adult salmonids radiotelemetry tracking at both JD ladders.
Approved by Jerry Carroll
Operation Project Manager
John Day Dam

## Birds
S2:
S1: No birds observed
S3:
P4:
P3: 25 DCC,5 merganser, 10 gulls
P2:
P1: NO birds observed
S4: up to 150 gulls in forebay and on wing wall

## AVGS
John Day:
| Temp: |  | Secchi: |  | Fallbacks
Sun | 43 |  | 6
Mon | 44 |  | 6
Tues | 44 |  | 6
Wed | 44 |  | 6
Thur | 43
Fri | 43 |  | 6
Sat | 44 |  | 6
AVG: | 43.5714 | AVG: | 6 | AVG | #DIV/0!
|  |  |  | MAX | 0
|  |  |  | MIN | 0
| NE1 | NE2 | S.Ent | SE1 | N.Ent | EW1 | JBS Diff | Bay1 | Bay19
Sun | 8.4 | 8.2 | 1.3 | 8.5 |  |  | 4.6 | 1.9 | 1.5
Sun
Mon | 8.2 | 8.2 | 1.2 | 8.5 |  |  | 4.6 | 2 | 2
Mon
Tues | 8.3 | 8.2 | 1.2 | 8.6 |  |  | 4.5 | 1.8 | 1.5
Tues
Wed | 8.9 | 8.9 | 1.3 | 8.4 |  |  | 4.6 | 1.7 | 1.5
Wed
Thur | 8.4 | 8.4 | 1.3 | 8.2 |  |  | 4.6 | 1.7 | 1.5
Thur
Fri | 8.5 | 8.2 | 1.2 | 8.3 |  |  | 4.6 | 1.7 | 1.5
Fri
Sat | 8.6 | 8.2 | 1.3 | 8.7 |  |  | 4.6 | 1.6 | 1.7
Sat
AVG: | 8.4714 | 8.3286 | 1.2571 | 8.4571 | #DIV/0! | #DIV/0! | 4.5857 | 1.7714 | 1.6