## SR
FISHWAY STATUS REPORT | [5 empty] | THE DALLES/JOHN DAY DAM
Date: | 2007-02-21 | [5 empty] | TD/JD/WC Project-Fisheries
Inspection Period: |  | 2/11 - 2/17/2007 |  |  |  |  | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541.296.7406
All areas are checked once a day. OOS = out of service
The Dalles Dam |  |  | Inspections | Criteria | Total Number of Inspections: | 7
|  |  | Out of Criteria | Limit | Comments
NORTH FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1' | Set at 1.0'.
Entrance differential |  |  | 0 | 1.0' - 2.0'
Entrance weir N1 |  |  | 0 | depth (≥ 8')
Entrance weir N2 |  |  |  |  | Closed.
PUD Intake differential |  |  | 0 | ≤ 0.5'
EAST FISHWAY |  |  |  |  | East ladder/entrances dewatered for annual inspection/maintenance. Return 2/23.
Exit differential |  |  | OOS | ≤ 0.5'
Removable weirs 154-157 |  |  | OOS |  | Preventative maintenance in progress
Weir 158-159 differential |  |  | OOS | 1.0' ± 0.1' | Rubber seals replaced on weir leafs
Count station differential |  |  | OOS | ≤ 0.3'
Weir crest depth |  |  | OOS | 1.0' ± 0.1'
Junction pool weir JP6 |  |  | OOS | depth (≥ 7')
East entrance differential |  |  | OOS | 1.0' - 2.0'
Entrance weir E1 |  |  | OOS
Entrance weir E2 |  |  | OOS | depth (≥ 8')
Entrance weir E3 |  |  | OOS | depth (≥ 8') | Structural modifications installed to improve reliability
Collection channel velocity |  |  | OOS | 1.5 - 4 fps
West entrance differential |  |  | OOS | 1.0' - 2.0'
Entrance weir W1 |  |  | OOS | depth (≥ 8')
Entrance weir W2 |  |  | OOS | depth (≥ 8')
Entrance weir W3 |  |  |  |  | Closed
South entrance differential |  |  | OOS | 1.0' - 2.0'
Entrance weir S1 |  |  | OOS | depth (≥ 8') | Structural modifications installed to improve reliability
Entrance weir S2 |  |  | OOS | depth (≥ 8') | Waiting for parts for weir repair
ICE/TRASH SLUICEWAY
Sluice gate operation |  |  |  | 1, 5, 18 | Endgate closed. Sluice gate at 1 and 18 open for forebay equalizing.
SPILLWAY |  |  |  |  | Closed
Pattern |  |  | 0 | per FPP
UnitPriority |  |  | 0 | per FPP
1% Efficiency of turbines |  |  | 0 | per FPP
John Day Dam |  |  | Inspections | Criteria | Total Number of Inspections: | 7
|  |  | Out of Criteria | Limit | Comments
NORTH FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Exit hydraulic weirs |  |  | 0 | open<263'
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1' | Set at 1.0'.
Entrance differential |  |  | 1 | 1.0' - 2.0' | 0.5'. Adjusted.
Entrance weir EW1 |  |  | 0 | depth (≥ 8') | Minor PLC calibration underway. Manually adjusted as needed.
Entrance weir EW2 |  |  |  |  | Closed.
SOUTH FISHWAY |  |  |  |  | South ladder/south entrance dewatered for annual inspection/maintenance. Return 2/28.
Exit differential |  |  | OOS | ≤ 0.5' | Several ladder expansion joints being repaired.
Hydraulic weir positions |  |  | OOS | low/mid/high | Preventative maintenance in progress.
Count station differential |  |  | OOS | ≤ 0.3' | Count window brush removed for maintenance.
Weir crest depth |  |  | OOS | 1.0' ± 0.1'
South entrance differential |  |  | OOS | 1.0' - 2.0'
Entrance weir SE1 |  |  | OOS | depth (≥ 8')
Collection channel velocity |  |  | OOS | 1.5 - 4 fps
Bay 1 differential |  |  | OOS | 1.0' - 2.0'
N.entrance PH(Bay 19)differential |  |  | OOS | 1.0' - 2.0'
Entrance weir NE1 |  |  | OOS | depth (≥ 8')
Entrance weir NE2 |  |  | OOS | depth (≥ 8')
JUVENILE BYPASS SYSTEM |  |  |  |  | 1/3 orifice open, rotated twice weekly.
Forebay/conduit differential |  |  | 0 | 4.0' - 5.0' | PLC box moved to improve reliability. Tainter gate set at 1.5
Submersible traveling screens |  |  | 0 | inspected | Stored in gatewells. Routine maintenance in progress.
SPILLWAY |  |  |  |  | Closed
Pattern |  |  | 0 | per FPP
Unit Priority |  |  | 0 | per FPP
1% Efficiency of turbines |  |  | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: | Dewatered for the season.
Maintenance: Preventative maintenance underway. Scheduled for return to operation 4/2.
Full flow PIT detection construction underway, all structural work to be completed by mid March.
OTHER ISSUES:
THE DALLES
Very low numbers of gulls, cormorants, and mergansers.
Avain lines over spillway to be modified mid March to cover spillbays 1-10. Lines temporarily removed over bays 1-6 for spillwall contractor.
Avian hazing contract in processing. Contract to start on month late (May 1) due to hiring problems.
Weir calibration and gatewell drawdown checks to resume in March.
Delays in material delivery for repair of S2 weir. Return to service estimate 4/1. S1 will be raised above 8' limit and manually adjusted to maintain
cirteria south entrance differential until S2 repairs complete. S2 will remain open without a weir.
MU16 scroll case dewatered 2/16 to inspect for possible oil leak; none was found. No fish found in the scroll case. Draft tube not dewatered.
Research: U of I adult radiotelemetry downloading continues. Project support for Spillway Improvement Study and adult PIT installation analysis
continues as needed.
JOHN DAY
Very low numbers of gulls, cormorants, and mergansers
Avian line replacements for broke lines to be installed mid March.
Avian hazing contract in processing. Contract to start on month late (May 1) due to hiring problems.
Weir calibration and gatewell drawdown checks to resume in March.
ROV dive inspection of collection channel grating, diffuser 5 intake trashrack and south fish turbine trashrack placement schedule for 2/28.
Planning and preparation underway for south fish turbine, gearbox and pump rehab. First of 3 to be completed during next winter outage period.
Research: U of I adult radiotelemetry downloading continues. Extensive project support of John Day configuration study continues. Project support
for north fishway improvement study and adult PIT installation analysis continues as needed.
Approved by;
Gene LaDouceur /s/
Project Manager
The Dalles/John Day/Willow Creek

## AVGS
The Dalles: |  | John Day:
Velocity: |  | Velocity:
AVG: | #DIV/0! | AVG: | #DIV/0!