## SR
FISHWAY STATUS REPORT |  |  |  | THE DALLES/JOHN DAY DAM
Date: 12/27/2008 | [5 empty] | TD/JD/WC Project-Fisheries
Inspection Period: 12/21 - 12/27/2008 | [5 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541.298.7406
One fishway inspection daily through Feb.
The Dalles Dam | Inspections | Criteria | Total Number of Inspections: | 4 | Temperature: |  | 39.875 | F
| Out of Criteria | Limit | Comments |  | Secchi: | 5.5 | Ft.
NORTH FISHWAY |  |  | North fish ladder scheduled dewatering 1/13/09; Return ~ 2/28/09.
Exit differential | 0 | ≤ 0.5'
Count station differential | 0 | ≤ 0.3'
Weir crest depth | 0 | 1.0' ± 0.1'
Entrance differential | 0 | 1.0' - 2.0'
Entrance weir N1 | 0 | depth (≥ 8') | Set at 9.5' depth.
Entrance weir N2 |  | Closed
PUD Intake differential | 0 | ≤ 0.5'
EAST FISHWAY |  |  | East fish ladder dewatered 12/2/08 for winter maintenance; Return ~ 1/08/09.
Exit differential |  | ≤ 0.5'
Removable weirs 154-157 |  | Per forebay | Preventative maintenance completed.
Weir 158-159 differential |  | 1.0' ± 0.1' | "
Count station differential |  | ≤ 0.3'
Weir crest depth |  | 1.0' ± 0.1'
Junction pool weir JP6 |  | depth (≥ 7')
East entrance differential |  | 1.0' - 2.0'
Entrance weir E1 |  | No criteria | Preventative maintenance completed.
Entrance weir E2 |  | depth (≥ 8') | "
Entrance weir E3 |  | depth (≥ 8') | "
Collection channel velocity |  | 1.5 - 4 fps
West entrance differential |  | 1.0' - 2.0'
Entrance weir W1 |  | depth (≥ 8') | Preventative maintenance completed.
Entrance weir W2 |  | depth (≥ 8') | "
Entrance weir W3 |  | No criteria | "
South entrance differential |  | 1.0' - 2.0'
Entrance weir S1 |  | depth (≥ 8') | Preventative maintenance completed.
Entrance weir S2 |  | depth (≥ 8') | "
JUVENILE PASSAGE
Sluicegate operation | 0 | units 1,5,18 | Endgate closed.
Turbine trashrack drawdown |  | <1.5', wkly | Resumes Apr 1
Spill volume |  | N/A | Spillway closed
Spill Pattern |  | N/A
Turbine Unit Priority |  | N/A
Turbine 1% Efficiency | 0 | per FPP
John Day Dam | Inspections | Criteria | Total Number of Inspections: | 4 | Temperature: |  | 40.25 | F
| Out of Criteria | Limit | Comments |  | Secchi: | 6 | Ft.
NORTH FISHWAY |  |  | North fish ladder scheduled dewatering 1/6/09; Return mid Feb.
Exit differential | 0 | ≤ 0.5'
Exit hydraulic weirs | 0 | Per forebay | Set for forebay >263'
Count station differential | 0 | ≤ 0.3'
Weir crest depth | 0 | 1.0' ± 0.1'
Entrance differential | 0 | 1.0' - 2.0'
Entrance weir EW1 | 0 | depth (≥ 8') | Average depth 8.1'.
Entrance weir EW2 | 0 | No criteria | Weir closed.
SOUTH FISHWAY |  |  | South fish ladder dewatered 12/3/08 for winter maintenance; Return ~ 12/ 31/08.
Exit differential |  | ≤ 0.5'
Hydraulic weir positions |  | Per forebay | Preventative maintenance underway
Count station differential |  | ≤ 0.3'
Weir crest depth |  | 1.0' ± 0.1'
South entrance differential |  | 1.0' - 2.0'
Entrance weir SE1 |  | depth (≥ 8') | Preventative maintenance underway
Collection channel velocity |  | 1.5 - 4 fps
Bay 1 differential |  | 1.0' - 2.0'
N.entrance PH (Bay 19)differential |  | 1.0' - 2.0'
Entrance weir NE1 |  | depth (≥ 8') | Preventative maintenance underway
Entrance weir NE2 |  | depth (≥ 8') | "
JUVENILE PASSAGE |  |  | Juvenile Bypass System dewatered 12/17/08; Return ~ 4/1/09.
Forebay/bypass conduit differential | 0 | 4.0' - 5.0' | Adjustment to 1/3 orifices open after STS removal completed. Rotated twice weekly.
Submersible traveling screens |  | N/A | Removal after Dec 15. Reinstall prior to Apr 1. Preventative maintenance underway.
Turbine trashrack drawdown |  | N/A | Resumes Apr 1
Vert barrier screen drawdown |  | N/A | Resumes Apr 1
Spill volume |  | N/A | Spillway closed
Spill pattern | 0 | per FPP
Turbine Unit Priority | 0 | per FPP | Operating units for maintenance purposes.
Turbine 1% Efficiency | 0 | per FPP
SMOLT MONITORING FACILITY
Operation: SMF dewatered 12/1/08, RTS ~ 4/1/09.
Maintenance:
Remove loose epoxy from elevated chute and smooth edges.
Repair separator tub corrosion.
Preventative maintenance of all mechanical equipment and tainter gate.
Engineer new bladder seal for switch gate to stop leakage. Procure and install prior to Apr 1.
OTHER ISSUES:
THE DALLES
Maintenance:
Preventative maintenance of all fishway mechanical equipment
Clean staff gauges and pickets.
Re-floor count station planning
Fish unit F1 overhaul underway (TDM/TDS)
Spillwall 8/9 construction continues. Coordination underway for concrete delivery and project access needs at north fishway
entrance area.
Research: Battelle sluiceway kelt/adult fallback study fall portion completed Dec 15. Spring half to study to resume Mar 1 - Apr 9.
University of Idaho adult salmonid telemetry downloading receivers weekly and conducting lamprey passage recording at count stations.
JOHN DAY
South fishladder on orifice flow, diffuser 5 opened Dec 18. Fish turbines return to service next week.
Maintenance:
South ladder dewatered Dec 3. The collection channels's diffuser gratings to be ROV inspected mid Jan.
Maintenance:
Preventative maintennce of all fishway mechanical equipment underway. South fishladder expansion joint repair (contract)
SE1 wall diffuser, assess condition and possible closure
Calibration: Entrance weirs, channel, tailwater, and exit staff gauges completed; all within criteria.
John Day north fishladder improvement study site visit mid Jan. Plans and specs underway for upper section. Construction scheduled next winter.
Research: The University of Idaho's adult salmonid telemetry crew is downloading receivers weekly.
approved by;
Tamera Armstrong/s/ project manager The Dalles Dam
Kimberley Oldham/s/ project manager John Day/Willow Creek Dams
Note on I9: g2opdrpc: 3 missed inspections due to incliment weather
Note on I46: g2opdrpc: 3 missed inspections due to inclement weather

## AVGS
The Dalles: | [5 empty] | John Day:
Temp: | 43 | Secchi: | 6 | Velocity: | N/A | Temp: | 43 | Secchi: | 6 | Velocity: | N/A
| 40 |  | 6 |  |  |  | 40 |  | 6
| 38.5 |  | 5 |  |  |  | 40 |  | 6
| 38 |  | 5 |  |  |  | 38 |  | 6
AVG: | 39.875 | AVG: | 5.5 | AVG: | #DIV/0! | AVG: | 40.25 | AVG: | 6 | AVG: | #DIV/0!