## SR
FISHWAY STATUS REPORT | [5 empty] | THE DALLES DAM
Date: 2/16/2010 | [7 empty] | The Dalles Project-Fisheries
Inspection Period: | 2/7 - 2/13/2010 | [6 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541-506-3800
Fishways are inspected once daily through Feb 28, 2010
The Dalles Dam |  | Inspections | Criteria | Total Number of Inspections: |  | 7 | Temperature: |  | 41.6571 | F
|  | Out of Criteria | Limit | Comments |  |  | Secchi: | 4.9286 | Ft.
NORTH FISHWAY |  |  |  | North ladder dewatered for annual maintenance Feb 8.
Exit differential |  |  | ≤ 0.5'
Count station differential |  |  | ≤ 0.3'
Weir crest depth |  |  | 1.0' ± 0.1'
Entrance differential |  |  | 1.0' - 2.0' | Average | On seal
Entrance weir N1 |  |  | depth (≥ 8') | Average | On seal
Entrance weir N2 |  |  | Closed | Bulkhead installed
PUD Intake differential |  |  | ≤ 0.5'
EAST FISHWAY |  |  |  | Watered up Feb 1; Fish Unit 1 in operation. Fish Unit 2 RTS Feb 8.
Exit differential |  | 0 | ≤ 0.5' |  |  | Daily differentials & weir depths, see AVGS tab below.
Removable weirs 154-157 |  | 0 | Per forebay
Weir 158-159 differential |  | 0 | 1.0' ± 0.1'
Count station differential |  | 0 | ≤ 0.3'
Weir crest depth |  | 0 | 1.0' ± 0.1'
Junction pool weir JP6 |  | 0 | depth (≥ 7')
East entrance differential |  | 1 | 1.0' - 2.0' | Average | 1.4 | 0.6' OOC; FU #1 in service, FU # 2 RTS Feb 8 pm.
Entrance weir E1 |  | 0 | No criteria | Average | 10.1833
Entrance weir E2 |  | 0 | depth (≥ 8') | Average | 10.4429
Entrance weir E3 |  | 0 | depth (≥ 8') | Average | 10.4429
Collection channel velocity |  | N/A | 1.5 - 4 fps
West entrance differential |  | 1 | 1.0' - 2.0' | Average | 1.1714 | 0.3' OOC; FU #1 in service, FU # 2 RTS Feb 8 pm.
Entrance weir W1 |  | 0 | depth (≥ 8') | Average | 8.7286
Entrance weir W2 |  | 0 | depth (≥ 8') | Average | 8.7143
Entrance weir W3 |  | 0 | No criteria | Average | closed.
South entrance differential |  | 1 | 1.0' - 2.0' | Average | 1.04 | 0.5' OOC; FU #1 in service, FU #2 RTS Feb 8 pm.
Entrance weir S1 |  | 0 | depth (≥ 8') | Average | 8.14
Entrance weir S2 |  | 0 | depth (≥ 8') | Average | 8.12
JUVENILE PASSAGE
Sluicegate operation |  | 0 | units 1,5,18 | Sluiceway closed Dec16 - Mar1. Endgate closed, sluicegate 1-1, 18-3 open to forebay.
Turbine trashrack drawdown |  | 0 | <1.5', wkly | To resume next juvenile passage season.
Spill volume |  | 0 | 40%, 24hr | Closed
Spill Pattern |  | 0 | per FPP | On seal. Spill patterns for 2010 finalized for Fish Passage Plan
Turbine Unit Priority |  | 0 | per FPP | Non passage season priority.
Turbine 1% Efficiency |  | 0 | per FPP
OTHER ISSUES:
THE DALLES
Birds:
Refer to "Birds" tab for maximum bird observations.
USDA hazing plan same as previous years, 7days/week May1-July30.
Planning logistics for avian line installation over spillway and east powerhouse first week of April. Spillway attachment points planned for bridge to
north shore and spillway.
Operations:
North fishway PUD aux water off Feb 6. The north fish ladder dewatered Feb 8. There were four adult steelhead, four juvenile steelhead, and one
adult Coho captured and released. The east fishway watered up Feb 1. |  |  |  |  | The Dalles Dam Fish Unit 2 outage extended to 1500 hours Monday,
Feb 8 due to exciter problems. The north entrance scheduled to be dewatered Feb 17.
Project fisheries providing support to the Inland Avian Predation Work Group meeting for basin wide standard abatement plan.
Fisheries waiting for confirmation on quagga/zebra mussel vulnerability assessment contract and will provide support as needed.
Fisheries, PUD, and Project Emergency Spill Coordinator planning sometime between Feb 27 - March 5 a test to determine the effectiveness of oil
containment and still maintain some fish passage. This will be accomplished by lowering the PUD tainter until vortices on the upstream side are
seen, assuming a vortex will suck oil under the gate. Also test will consist of only one sluice gate open on the bypass to see if reduced flow is better.
Maintenance:
Awaiting brush removal contract for north fishway and south fish channel.
The east fishway expansion joints sealing attempt failed. Engineering investigating considering new plan for next winter outage.
The transformer oil spill update:
Action plan in place if oil progressed to south fish channel. Plan provided to FPOM members. Description of the problem: There remains some
uncertainty how much oil is still under the spill site. Oil was found in four drain holes leading into the sluiceway. Therefore we are required by
regulating agencies to install the grout curtain to prevent further oil from entering the river via the sluiceway. The planning team is working to complete
in Feb., and have sluiceway open Mar 1 for Battelle's research. The sluiceway cannot be opened until this grout curtain has been installed.
entering the river via sluiceway. The planning team is working to complete in Feb, but contractor requesting to keep sluiceway closed through
Mar 8.
Type of outage required; ITS closed through 8 March 2010. The contractor shall construct a grout curtain beneath and along the sides of the ice
and trash sluiceway. The sluiceway is only accessible by crane. Because the sluiceway is only dewatered until Mar 1, work within the sluiceway
is time critical. Sequencing of the work shall be grouting beneath the floor slab followed by grouting behind the walls. It is less desirable, but
grouting of the sides could be done by angling grout holes down towards the intersect the sluiceway wall from above outside the sluiceway.
Drilling from outside will require greater drilling depths. The goal is to use controlled grouting techniques to create a narrow (5') wide zone of
grouted rock 30' deep beneath and around the sides of the sluiceway. Grouting pressures shall be tightly controlled to prevent damage to
the concrete walls and floor slobs. Grouting volume shall be tightly controlled to prevent migration beyond twice the width of the zone to prevent
grout from penetrating into drains and into the nearby fishway. No more than one drain may be filled with grout. The grout curtain shall be
constructed beneath the riverward side of the sluiceway bridge. It may be necessary to do the work beneath the bridge because the abutment for
the sluiceway across the fishway is located immediately downstream of the access bridge. The grout curtain shall be positioned immediately
between two wall drains and run perpendicular to the sluiceway.
Bay 8-9 spillwall:
General Construction Company (GCC) status of season two work is: Pre-drill holes complete, re-drilled holes (99%), successful water tested
holes (99%), tendons installed (87%), tendons first stage grouted (85%), tendons stressed (71%), and second stage grouted (63%). The last
week of GCC dives starts Feb 16. The PUD will occupy the spillwall 1 - 2 bridge with a 45 ton crane from Feb 20 - 21. GCC will use native drill
tailings to fill a pond in a north bone year. Diving is scheduled for Feb 15 - 19.
North exit debris guard repaired from wind damage. Rails to be installed mid Feb via dive. Debris guard to be installed prior to north ladder water up.
Research: Battelle Kelt/Adult steelhead sluiceway passage study ongoing. Sluiceway closed Dec15 and turbine passage to be monitored
through Mar 1. Sluiceway will re-open for passage monitoring Mar 1-Apr 9 and will remain open through remainder of juvenile passage season.
Planned turbine unit 1-4 maintenance outage to affect Spring data from Mar15-Apr1. Westrick oil recovery efforts may delay sluiceway open to Mar8.
Planning continues for research equipment installations for 2010 passage evaluation season, including dive installation of pipes to support
JSAT hydrophones. Installation dates mid Feb through first week of March.
Approved by Ron D. Twiner, OPM
The Dalles Lock and Dam

## Birds
P6: Two cormorants.
P5:
P4: Seven bald eagles.
S2:
S3:
S1: Seven cormorants on rocks.
F7: Eight cormorants, six coots, two gulls, and one Canada goose.

## AVGS
The Dalles:
Temp: | 42 | Secchi: | 4
| 42 |  | 5
| 41.8 |  | 5
| 41.4 |  | 5
| 41.4 |  | 5
| 41 |  | 5
| 42 |  | 5.5
AVG: | 41.6571 | AVG: | 4.9286
| North Fish Ladder |  | East Fish Ladder
| North Entrance |  | East Entrance |  |  |  | West Entrance |  |  |  | South Entrance
Day: | Differential | N1 Depth | Differential | E1Depth | E2 Depth | E3 Depth | Differential | W1Depth | W2 Depth | W3 Depth | Differential | S1 Depth | S2 Depth | % Spill
Sunday | Orifice flow |  | 1.4 |  | 10 | 10.4 | 1 | 8 | 8 | One Fish Unit in operation.
Monday | Dewatered |  | 1.5 | 10 | 10 | 10.5 | 1.2 | 8.1 | 8 | One Fish Unit in operation.
Tuesday |  |  | 0.6 | 10.1 | 10 | 10 | 0.3 | 9 | 9 | closed | 0.5 | 8.2 | 8.1
Wednesday |  |  | 1.8 | 10 | 10 | 10 | 1.6 | 8.9 | 8.9 |  | 1.4 | 8.2 | 8.1
Thursday |  |  | 1.6 | 11 | 11 | 9.9 | 1.3 | 9 | 9.1 |  | 0.7 | 8.1 | 8.2
Friday |  |  | 1.4 | 10 | 11 | 11 | 1.4 | 9 | 8.9 |  | 1.3 | 8.1 | 8.1
Saturday |  |  | 1.5 | 10 | 11.1 | 11.1 | 1.4 | 9.1 | 9.1 |  | 1.3 | 8.1 | 8.1
AVG: | On seal | On seal | 1.4 | 10.1833 | 10.4429 | 10.4143 | 1.1714 | 8.7286 | 8.7143 | closed. | 1.04 | 8.14 | 8.12 | On seal