## SR
FISHWAY STATUS REPORT | [6 empty] | THE DALLES DAM
Date: | 2010-03-01 | [7 empty] | The Dalles Project-Fisheries
Inspection Period: |  | 2/21 - 2/27/2010 | [6 empty] | P.O. Box 564
The Dalles, OR 97058-9998
Phone: 541-506-3800
Fishways are inspected twice daily.
The Dalles Dam |  |  | Inspections | Criteria | Total Number of Inspections: |  | 7 | Temperature: |  | 41.8429 | F
|  |  | Out of Criteria | Limit | Comments |  |  | Secchi: | 5.2143 | Ft.
NORTH FISHWAY |  |  |  |  | North ladder dewatered for annual maintenance Feb 8. ETR last week of Feb.
Exit differential |  |  |  | ≤ 0.5'
Count station differential |  |  |  | ≤ 0.3'
Weir crest depth |  |  |  | 1.0' ± 0.1'
Entrance differential |  |  |  | 1.0' - 2.0'
Entrance weir N1 |  |  |  | depth (≥ 8')
Entrance weir N2 |  |  |  | Closed | Bulkhead installed
PUD Intake differential |  |  |  | ≤ 0.5'
EAST FISHWAY
Exit differential |  |  | 0 | ≤ 0.5'
Removable weirs 154-157 |  |  | 2 | Per forebay | Auto adjusts at 1' increments. |  | 156 OOC at 158.2, 158.6; auto adj. during inspection.
Weir 158-159 differential |  |  | 0 | 1.0' ± 0.1'
Count station differential |  |  | 0 | ≤ 0.3'
Weir crest depth |  |  | 0 | 1.0' ± 0.1'
Junction pool weir JP6 |  |  | 0 | depth (≥ 7') | Manually adjusted as needed.
East entrance differential |  |  | 0 | 1.0' - 2.0' | Average | 1.3833 | Daily differentials & weir depths, see AVGS tab below.
Entrance weir E1 |  |  | 0 | No criteria | Average | 9.3333 | Manually adjusted.
Entrance weir E2 |  |  | 0 | depth (≥ 8') | Average | 11.7
Entrance weir E3 |  |  | 0 | depth (≥ 8') | Average | 11.6
Collection channel velocity |  |  | 0 | 1.5 - 4 fps | Average | N/A
West entrance differential |  |  | 0 | 1.0' - 2.0' | Average | 1.4667
Entrance weir W1 |  |  | 0 | depth (≥ 8') | Average | 8.7333
Entrance weir W2 |  |  | 0 | depth (≥ 8') | Average | 8.9833
Entrance weir W3 |  |  | 0 | No criteria | Average | Closed
South entrance differential |  |  | 0 | 1.0' - 2.0' | Average | 1.3
Entrance weir S1 |  |  | 0 | depth (≥ 8') | Average | 8.0833
Entrance weir S2 |  |  | 0 | depth (≥ 8') | Average | 8.15
JUVENILE PASSAGE
Sluicegate operation |  |  |  | units 1,5,18 | Sluiceway closed Dec16 - Mar8. Endgate closed, sluicegate 18-3 open to forebay.
Turbine trashrack drawdown |  |  |  | <1.5', wkly | To resume Apr1 for juvenile passage season.
Spill volume |  |  |  | 40%, 24hr | Closed.
Spill Pattern |  |  |  | per FPP | On seal. Spill patterns for 2010 finalized for Fish Passage Plan
Turbine Unit Priority |  |  | 0 | per FPP | Non passage season priority.
Turbine 1% Efficiency |  |  | 0 | per FPP
OTHER ISSUES:
THE DALLES
Birds:
Refer to "Birds" tab for maximum bird observations.
USDA hazing plan same as previous years, 7days/week May 1 - July 30.
Planning logistics for avian line installation over spillway and east powerhouse first week of April. Spillway attachment points planned for bridge to
north shore and spillway. Installation expected first week of April.
Operations:
Project fisheries providing support to Inland Avian Predation Work Group for basin wide standard abatement plan. In process of compiling historical
data into a consolidated data base for Bonneville, The Dalles and John Day. Work group will review and determine standards for data collection.
Outline for Zebra/Quagga Mussels Monitoring and Control plan completed. Due to elevated risk of colonization in Columbia River, monitoring and
risk assessment efforts will be increased. Monitoring will include weekly checks of sample units in each ladder, and biweekly plankton tow sampling
after water temps exceed 50F. Risk assessment will include contract with RNT Consulting Inc to evaluate vulnerable areas of project.
Calibrations completed Feb 23 on entrance weirs, channel, and tailwater, and exit staff gauges. All in criteria except west entrance channel which
was out of criteria by 0.1'.
Maintenance:
The north fish ladder entrance was dewatered Feb 23. Two juvenile Chinook removed and released to tailrace.
Concrete 2" radius for lamprey passage improvement at south entrance completed Feb 24. North fishway winter maintenance completed.
Brush trimming from inside fishladder completed. North fishway returned to service Feb 27.
Awaiting brush removal contract for north fishway and south fish channel to remove trees that have potential of falling into fishway.
The transformer oil spill update:
Grout curtain is being installed in the Ice/Trash Sluiceway and to be completed next week. Sluiceway to be opend Mar 8.
Bay 8-9 spillwall:
General Construction Company (GCC) status of season two work is:
Contractor continuing dry finishing operations. Segment 14 leveling cap placement was completed Feb 25, and segment 15 scheduled for
completion March 2. The final underwater baseline inspection scheduled for completion this week.
Research: Battelle Kelt/Adult steelhead sluiceway passage study ongoing. Original plan was for sluiceway closure and turbine passage monitoring
through Mar 1. Sluiceway will now re-open Mar 8 due to westrick oil spill work. It will remain open through remainder of juvenile passage season.
Planned turbine unit 1-4 maintenance outage will also affect Spring data from Mar15-Apr1.
Dive installation of JSAT pipes completed on spillway and PUD intake and started on powerhouse. Expected to be completed ahead of schedule.
Approved by Ron D. Twiner, OPM
The Dalles Lock and Dam

## Birds
P6: One cormorant.
P5:no birds
P4:no birds
S2:no birds
S3:no birds
S1: Seven cormorants on rocks.
F7: no birds

## AVGS
The Dalles:
Temp: | 42 | Secchi: | 5
| 42 |  | 5
| 41.8 |  | 5
| 41.7 |  | 6
| 41.4 |  | 5
| 42 |  | 5
| 42 |  | 5.5
AVG: | 41.8429 | AVG: | 5.2143
| North Fish Ladder |  | East Fish Ladder
| North Entrance |  | East Entrance |  |  |  | West Entrance |  |  |  | South Entrance
Day: | Differential | N1 Depth | Differential | E1Depth | E2 Depth | E3 Depth | Differential | W1Depth | W2 Depth | W3 Depth | Differential | S1 Depth | S2 Depth | % Spill
Sunday |  |  | 1.2 | 11 | 12 | 12 | 1.3 | 9 | 9 |  | 1.3 | 8.1 | 8.1
Monday |  |  | 1.4 | 9 | 12.1 | 12 | 1.5 | 9 | 9 |  | 1.3 | 8.1 | 8.2
Tuesday |  |  | 1.5 | 8.9 | 11.4 | 11.5 | 1.5 | 8.9 | 9.1 |  | 1.3 | 8.1 | 8.1
Wedsday | Dewatered Feb 8 |  | 1.4 | 9 | 11.6 | 11.5 | 1.5 | 8.4 | 9 |  | 1.3 | 8.1 | 8.1
Thursday |  |  | Fish Units 1 and 2 OOS for trolley pipe installation for Battelle's study
Friday |  |  | 1.3 | 9.1 | 11.6 | 11.5 | 1.5 | 8.6 | 9.1 |  | 1.3 | 8.1 | 8.2
Saturday |  |  | 1.5 | 9 | 11.5 | 11.1 | 1.5 | 8.5 | 8.7 |  | 1.3 | 8 | 8.2
AVG: | On seal | On seal | 1.3833 | 9.3333 | 11.7 | 11.6 | 1.4667 | 8.7333 | 8.9833 | Closed | 1.3 | 8.0833 | 8.15 | On seal

## TD north ladder
Concrete grinding 2" radius north fish ladder entrance to improve lamprey passage.