## Sheet1
Version
12_22_2016 |  |  | FY17 Willamette BiOp PDT Engineering Milestones & Regional Review Schedule
|  |  | October | November | December | January | February | March | April | May | June | July | August | September
COUGAR DOWNSTREAM PASSAGE | EDR | 30%
60%
90%
| DDR | 30%
60%
90%
| P&S | 30%
60%
90%
DETROIT TEMPERATURE CONTROL | EDR | 30%
60%
90%
| DDR | 30%
60%
90%
| P&S | 30%
60%
90%
DETROIT DOWNSTREAM PASSAGE | EDR | 30%
60%
90%
| DDR | 30%
60%
90%
| P&S | 30%
60%
90%
FOSTER FISH WEIR | EDR | 30%
60%
90%
| DDR | 30%
60%
90%
| P&S | 30%
60%
90%
Willamette Fish Facility Design Review Working Group (WFFDRWG) Meetings |  |  | Meeting Date |  | December 6th | January 10th* | February 14th | March 7th | April 4th | May 2nd | June 6th | July 11th | August 1st | September 5th
|  |  | Agenda Topics |  | Cougar 90%EDR | Foster DDR/P&S 60%
[5 empty] | Detroit 90% EDR | Cougar DDR
* special WFFDRWG meeting in January for Detroit (date TBD)
WATER REVIEW
WATER REVIEW
WFFRDWG BRIEF
WATER REVIEW
WATER REVIEW
WATER REVIEW
WATER REVIEW DATE TBD