Water Management Plan 						Appendix 3

Introduction to Timeline

The timeline given below shows the approximate starting and end times of actions and events

included in this year’s Water Management Plan.  It is designed to give a sense of when various

actions occur.  Dates are approximate and subject to change.  Also note actions shown may not

occur.

Project Abbreviations

LIB – Libby

HGH – Hungry Horse

LWG – Lower Granite

LGS – Little Goose

LMN – Lower Monumental

IHR – Ice Harbor

MCN – McNary

JDA – John Day

TDA – The Dalles

BON – Bonneville

TMT – Technical Management Team

DWR – Dworshak

PRD – Priest Rapids

ALF – Albeni Falls

GCL – Grand Coulee

RCC – Reservoir Control Center

RFC – River Forecast Center

USBR – US Bureau of Reclamation

| ID | Task Name | Start | Finish |
| --- | --- | --- | --- |
| 1 | LIB Operate to Minimum Flows / Ramp Rates | 10/1/15 | 9/30/16 |
| 2 | HGH Operate to Minimum Flows / Ramp Rates | 10/1/15 | 9/30/16 |
| 3 | TMT Assess Potential of Providing Flow for Chinook Below BON | 10/1/15 | 11/30/15 |
| 4 | TMT Assess Potential of Providing Flow for Chum Below BON | 10/1/15 | 11/30/15 |
| 5 | TMT Preliminary Discussions of Flood Control / Refill | 10/1/15 | 10/1/15 |
| 6 | TMT Albeni Falls Fall / Winter Draw Down Discussions | 10/1/15 | 10/1/15 |
| 7 | Hanford Reach / Vernita Bar Flows Set (Non-BiOp) | 10/1/15 | 10/1/15 |
| 8 | DWR Operate at Minimum Outflow | 10/1/15 | 9/30/16 |
| 9 | PRD Vernita Bar Protection Flows (Non-BiOp) | 10/1/15 | 5/9/16 |
| 10 | MCN Waterfowl Hunting Enhancement (Non-BiOp) | 10/1/15 | 1/31/16 |
| 11 | LIB Storage May be Used to Support Chum Flows | 11/2/15 | 2/23/16 |
| 12 | HGH Storage May be Used to Support Chum Flows | 11/2/15 | 2/23/16 |
| 13 | ALF Storage May be Used to Support Chum Flows | 11/2/15 | 2/23/16 |
| 14 | GCL Storage May be Used to Support Chum Flows | 11/2/15 | 2/23/16 |
| 15 | DWR Storage May be Used to Support Chum Flows | 11/2/15 | 2/23/16 |
| 16 | BON Provide Chum Tailwater | 11/1/15 | 4/10/16 |
| 17 | TMT Determine Winter / Spring Chum Flow Levels | 10/1/15 | 4/10/16 |
| 18 | HEPB Determine Flood Control / Refill Strategies | 12/1/15 | 4/16/16 |
| 19 | HEPB Determine Flood Control Shifts | 12/1/15 | 4/16/16 |
| 20 | LIB Operate to Flood Control Curve | 12/1/15 | 6/30/16 |
| 21 | DWR Operate to Flood Control Curve | 12/1/15 | 6/30/16 |
| 22 | ALF Operate to Flood Control Curve | 9/10/15 | 6/22/16 |
| 23 | GCL Operate to Flood Control Curve | 12/1/15 | 6/30/16 |
| 24 | HGH Operate to Flood Control Curve | 12/1/15 | 6/30/16 |
| 25 | ARDB Whitefish Flows 45-55 kcfs (non-BiOp) | 12/1/15 | 1/31/16 |
| 26 | LIB Burbot Flows 6-8 kcfs (non-BiOp) | 10/1/15 | 2/28/16 |
| 27 | ARDB 1 MAF Flow Augmentation Filling | 1/1/16 | 4/25/16 |
| 28 | RFC January Final Forecast | 1/8/16 | 1/8/16 |
| 29 | TMT Begin Spring Transport Discussions | 3/1/16 | 3/1/16 |
| 30 | TMT Hanford Reach Operations Discussions (non-BiOp) | 2/1/16 | 2/1/16 |
| 31 | RFC February Final Forecast | 2/5/16 | 2/5/16 |
| 32 | USBR Min. Flows from HGH and at Columbia Falls Set | 3/1/16 | 3/1/16 |
| 33 | BON Spring Creek Hatchery Release from Bon Hatch (non-BiOp) | 4/1/16 | 4/30/16 |
| 34 | RFC March Final Forecast | 3/7/16 | 3/7/16 |
| 35 | LWG Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 36 | LGS Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 37 | LMN Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 38 | IHR Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 39 | MCN Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 40 | JDA Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 41 | TDA Operate to 1% Peak Efficiency | 4/1/16 | 10/31/16 |
| 42 | BON Operate Units in Accordance with the Fish Passage Plan | 4/1/16 | 10/31/16 |
| 43 | MCN Protect Nesting Waterfowl (non-BiOp) | 3/1/16 | 5/31/16 |
| 44 | LIB Start Operational Plan | 4/1/16 | 4/1/16 |
| 45 | HGH Start Operational Plan | 4/1/16 | 4/1/16 |
| 46 | TDA Wasco Co. Sampling Tuesdays (non-BiOp) | 4/1/16 | 8/29/16 |
| 47 | USBR Upper Snake Augmentation Determined | 4/1/16 | 4/1/16 |
| 48 | PRD Hanford Reach Protection Flows (non-BiOp) | 4/1/16 | 6/28/16 |
| 49 | ARDB Trout Spawning Flows 15-25 kcfs (non-BiOp) | 4/1/16 | 6/28/16 |
| 50 | LWG Spring Flow Objective | 4/3/16 | 6/20/16 |
| 51 | LWG MOP Operation | 4/3/16 | 8/31/16 |
| 52 | LGS MOP Operation | 4/3/16 | 8/31/16 |
| 53 | LMN MOP Operation | 4/3/16 | 8/31/16 |
| 54 | IHR MOP Operation | 4/3/16 | 8/31/16 |
| 55 | LWG Spill for Juvenile Fish Operation | 4/3/16 | 8/31/16 |
| 56 | LGS Spill for Juvenile Fish Operation | 4/3/16 | 8/31/16 |
| 57 | LMN Spill for Juvenile Fish Operation | 4/3/16 | 8/31/16 |
| 58 | IHR Spill for Juvenile Fish Operation | 4/3/16 | 8/31/16 |
| 59 | RFC April Final Forecast | 4/8/16 | 4/8/16 |
| 60 | TMT Set Flow Objectives / Refill Strategy | 4/7/16 | 4/7/16 |
| 61 | LIB at April 10 Flood Control Elevation | 4/10/16 | 4/10/16 |
| 62 | GCL at April 10 Flood Control Elevation | 4/10/16 | 4/10/16 |
| 63 | DWR at April 10 Flood Control Elevation | 4/10/16 | 4/10/16 |
| 64 | HGH at April 10 Flood Control Elevation | 4/10/16 | 4/10/16 |
| 65 | ALB at April 10 Flood Control Elevation | 4/10/16 | 4/10/16 |
| 66 | MCN Spring Flow Objective | 4/10/16 | 6/30/16 |
| 67 | PRD Spring Flow Objective | 4/10/16 | 6/30/16 |
| 68 | JDA Minimum Irrigation Pool | 4/10/16 | 9/30/16 |
| 69 | MCN Spill for Juvenile Fish Passage | 4/10/16 | 8/31/16 |
| 70 | JDA Spill for Juvenile Fish Passage | 4/10/16 | 8/31/16 |
| 71 | TDA Spill for Juvenile Fish Passage | 4/10/16 | 8/31/16 |
| 72 | BON Spill for Juvenile Fish Passage | 4/10/16 | 8/31/16 |
| 73 | HGH Operational Plan Due | 11/17/16 | 11/17/16 |
| 74 | LIB Operational Plan Due | 5/3/16 | 5/3/16 |
| 75 | LIB Sturgeon Pulse | 5/16/16 | 6/30/16 |
| 76 | ARDB 1MAF Flow Augmentation Drafting (non-BiOp) | 5/3/16 | 7/29/16 |
| 77 | RFC May Final Forecast | 5/6/16 | 5/6/16 |
| 78 | TMT Determine Volume of Water Available for Sturgeon Pulse | 5/1/16 | 5/1/16 |
| 79 | RFC June Final Forecast | 6/7/16 | 6/7/16 |
| 80 | TMT Determine Summer Flow Objective | 6/7/16 | 6/7/16 |
| 81 | DWR Temperature Modeling and Release Strategy | 6/15/16 | 6/15/16 |
| 82 | Start Work on Next Year’s Water Management Plan | 6/15/16 | 6/15/16 |
| 83 | LWG Summer Flow Objective | 6/21/16 | 8/31/16 |
| 84 | LIB Refill by June 30 | 6/30/16 | 6/30/16 |
| 85 | GCL Refill by June 30 | 6/30/16 | 6/30/16 |
| 86 | DWR Refill by June 30 | 6/30/16 | 6/30/16 |
| 87 | HGH Refill by June 30 | 6/30/16 | 6/30/16 |
| 88 | ALF Refill by June 30 | 6/30/16 | 6/30/16 |
| 89 | LIB Operate to Meet Summer Flow Objectives | 7/1/16 | 8/31/16 |
| 90 | GCL Operate to Meet Summer Flow Objectives | 7/1/16 | 8/31/16 |
| 91 | HGH Operate to Meet Summer Flow Objectives | 7/1/16 | 8/31/16 |
| 92 | ALF Operate to Meet Summer Flow Objectives | 7/1/16 | 8/31/16 |
| 93 | DWR Operate to Meet Summer Flow Objectives | 7/1/16 | 8/31/16 |
| 94 | MCN Summer Flow Objective | 7/1/16 | 8/31/16 |
| 95 | GCL Operate Banks Lake 5 ft. from Full | 7/1/16 | 8/31/16 |
| 96 | LIB Bull Trout Releases | 7/1/16 | 8/1/16 |
| 97 | LIB Libby / Arrow Swap Considered | 7/1/16 | 7/1/16 |
| 98 | RFC July Final Forecast | 7/8/16 | 7/8/16 |
| 99 | DWR Draft to Elevation 1535 feet | 8/31/16 | 8/31/16 |
| 100 | GCL Summer Draft Limit 1280 or 1278 ft. | 8/31/16 | 8/31/16 |
| 101 | GCL Banks Lake Drafted to 1565 ft. | 8/31/16 | 8/31/16 |
| 102 | LIB Draft to 10 Feet from Full *except in lowest 20th percentile water years | 9/30/16 | 9/30/16 |
| 103 | HGH Summer Draft Limit 3540 ft. | 9/30/16 | 9/30/16 |
| 104 | DWR Draft to elevation 1520 feet | 9/30/16 | 9/30/16 |
| 105 | DWR Operate to Minimum Outflow | 9/1/16 | 9/30/16 |
| 106 | GCL Kokanee Forebay Elevation 1283 ft. (non-BiOp) | 9/30/16 | 9/30/16 |